# Multi-mesh support for OSMOSE-Python — implementation plan

Date: 2026-04-27 Status: plan, no code committed Companion to: docs/superpowers/specs/2026-04-24-non-rectangular-grids-exploration.md (feasibility study) Author: plan distilled from grid-topology survey + 2026-04-24 hex/FEM exploration

The 2026-04-24 feasibility study answered “is it possible?” (yes, in three flavours). This plan answers “if we commit, what are the option packages we can pick from, what does each ship, and in what order?”. Five concrete option packages are described, sized, and contrasted; a sixth — “do nothing” — is the implicit baseline.

## TL;DR — picking from the menu

| # | Package | Engine impact | Cost | Ships when | Best for |
| --- | --- | --- | --- | --- | --- |
| A | Curvilinear-rectangular only | Minimal | 1–2 wk | now | Coupling with NEMO/ROMS-style ocean models |
| B | Topology abstraction (no new mesh) | Refactor | 2–3 wk | now | Cleanup that unblocks all later options without forking parity |
| C | A + B + Hex (H3) grid | New topology | 6–8 wk | next quarter | Cleaner dispersal kernels, hierarchical refinement |
| D | A + B + Unstructured UGRID mesh | New topology + I/O | 3–4 mo | next half | Coastal lagoon/estuary refinement |
| E | Pre-processor only (mesh→rect aggregator) | None | 1–2 wk | now | Use external mesh data without touching engine |
| F | Nested-rectangular subgrids (AMR-lite) | Engine-internal | 4–6 wk | next quarter | Refine specific zones (e.g., Vistula Lagoon) without leaving the rectangular world |

Recommendation: ship B unconditionally (it’s a refactor with no behavior change and it pays for itself in code-quality + testability), then defer the choice between A, C, D, F to a domain-driven decision based on the use case. E is parallel and complementary to all others.

The Java-parity question is the single most consequential strategic decision. Options B and E preserve parity. A, C, D, F all break it.

## 0 · Where the engine is today (minimal recap)

osmose/engine/grid.py:16-122 defines a single Grid class with hardcoded (ny, nx) 2D layout, row-major indexing (cell_id = y*nx + x), and 8-connectivity via integer (dy, dx) ∈ {-1,0,1}² arithmetic. Cell topology assumptions leak into:

- osmose/engine/processes/movement.py:33-193 — random walk + map CSV

- osmose/engine/processes/mortality.py:1788-1805 — cell grouping via cell_y * grid.nx + cell_x

- osmose/engine/output.py:492-640 — NetCDF writer with (time, species, lat, lon) dims

- ui/pages/grid_helpers.py:289-707 — polygon construction from meshgrid

- osmose/schema/grid.py:5-98 — grid.nlon, grid.nlat, bounding-box config keys

The engine already separates cell-local (predation, forcing, fishing) from cell-topology (movement, neighbors, output) logic. That separation is what makes any of the five options below tractable.

A subtle gotcha caught in the 2026-04-24 study and re-verified for this plan: Grid.from_netcdf() at grid.py:108-112 reads 2D latitude/longitude arrays from input NetCDFs but immediately collapses them to 1D via lat = lat[:, 0]. So OSMOSE-Python today claims curvilinear support but silently drops the across-row lat/lon variation. Option A starts by fixing this lie.

## 1 · Option A — Curvilinear-rectangular only

What it ships: OSMOSE-Python correctly consuming a 2D (ny, nx) latitude/longitude NetCDF — i.e., grids where cell centers don’t sit on a regular lat-lon lattice. Used by NEMO, ROMS, POM, MOM, FVCOM, and Copernicus-Marine product grids.

What it does NOT change: Cell adjacency (still 8-connected (dy, dx)), cell ID scheme (still row-major), random walk semantics (still index-space), map CSV format (still 2D matrices). Internally the engine continues to think it has a regular (ny, nx) grid.

Concrete tasks (sized in days):

| # | Task | Files | Days |
| --- | --- | --- | --- |
| A.1 | Stop collapsing 2D lat/lon to 1D in Grid.from_netcdf | grid.py:108-112 | 0.5 |
| A.2 | Store lat2d, lon2d optional fields on Grid | grid.py:16-44 | 0.5 |
| A.3 | Output writer: emit latitude(ny,nx) + longitude(ny,nx) per CF when curvilinear | output.py:492-640 | 1.5 |
| A.4 | UI overlay: pass curvilinear lat/lon through to polygon_layer (already partly supported) | ui/pages/grid_helpers.py:469-518 | 1 |
| A.5 | Schema: add grid.curvilinear: bool flag, drop grid.upleft.* requirement when true | osmose/schema/grid.py:5-98 | 0.5 |
| A.6 | Test fixture: ROMS-style 30×40 distorted grid; end-to-end Baltic-shaped run | tests/test_curvilinear_grid.py (new) | 2 |
| A.7 | Movement docstring + warning: “displacement is in cell-index space, not km” | movement.py:163-193 | 0.5 |
| A.8 | Update docs/parity-roadmap.md: curvilinear is a Java-divergence | docs/parity-roadmap.md | 0.5 |

Effort: 7 person-days = ~1.5 weeks.

Pros: - Smallest change that unlocks coupling to widely-used ocean-model output (NEMO, ROMS). - No engine logic touched. - Zero risk to existing rectangular runs.

Cons: - Doesn’t help the dispersal-kernel-correctness question — random walk still in index space. - Forces UI maintainers to handle two polygon-construction code paths. - Breaks Java parity the moment a curvilinear grid is loaded — Java-OSMOSE has no curvilinear support.

When to pick: there is a concrete external dataset (e.g., a Copernicus Marine product, a NEMO-Baltic run) that we want to drive Baltic-OSMOSE forcing from, and which provides (ny, nx) 2D lat/lon. Otherwise this is busywork until Option B or E lands.

## 2 · Option B — Topology abstraction (no new mesh)

What it ships: A GridTopology protocol that the engine talks to instead of Grid. The current rectangular grid becomes the first implementation. No behavioral change. Every test passes byte-for-byte. But every place in the engine that previously did y * nx + x arithmetic now goes through the protocol.

Why this is the foundation: without B, options C/D/F all require 2× more invasive changes. With B, each new topology is a ~200-LOC subclass (plus its movement kernel + UI rendering) and slots into the existing engine.

Concrete tasks:

| # | Task | Files | Days |
| --- | --- | --- | --- |
| B.1 | Define GridTopology Protocol (n_cells, ocean_mask, lat, lon, neighbors, random_neighbor, walk_k_ring, cell_to_xy_or_None) | osmose/engine/grid_topology.py (new) | 1 |
| B.2 | Port Grid → RectangularGrid implementing the protocol | osmose/engine/grid.py | 1.5 |
| B.3 | Mortality: replace cell_y * grid.nx + cell_x with topology.cell_id(cy, cx) | mortality.py:1788-1805 | 0.5 |
| B.4 | Movement random walk: factor neighbor selection into topology method | movement.py:163-193 | 1.5 |
| B.5 | Movement maps: keep 2D CSV reader; add per-cell CSV reader; topology decides which | movement.py:33-103 | 2 |
| B.6 | Output writer: branch on topology kind for spatial NetCDF dimensions | output.py:492-640 | 1.5 |
| B.7 | UI: introduce build_grid_layers(topology) dispatch; rectangular path unchanged | ui/pages/grid_helpers.py:289-707 | 2 |
| B.8 | Schema: grid.type ∈ {rectangular} (placeholder for future values); existing keys unchanged | osmose/schema/grid.py | 0.5 |
| B.9 | Property-test parity: pre/post refactor must produce identical biomass + diet outputs on EEC + Baltic 5-y runs | tests/test_grid_topology_parity.py (new) | 2 |
| B.10 | Documentation: how to add a new topology | docs/architecture/grid-topologies.md (new) | 0.5 |

Effort: 13 person-days = ~2.5 weeks.

Pros: - No behavior change. All existing tests stay green; user-visible behavior is unchanged. - Cleans up the implicit (y, x) tuple everywhere — much easier to reason about. - Pre-pays the refactor cost for all later options (C, D, F). - Can ship independently and ship today if approved.

Cons: - Ships nothing user-visible. Hard to “sell” to a non-engineer stakeholder. - 2.5 weeks for “no change” feels expensive; need to frame as enabling investment.

When to pick: unconditionally. The only argument against B is “we’ll never want non-rectangular” — and even then the abstraction tightens an under-modelled boundary.

## 3 · Option C — Hexagonal H3 grid (depends on B)

What it ships: A HexGridTopology implementation backed by Uber’s H3 indexing library. Cells are regular hexagons at a chosen resolution (H3 levels 5–7 ≈ 8.5 km², 1.2 km², 0.17 km² respectively). 6-connectivity, uniform nearest-neighbor distance, hierarchical refinement, and battle-tested geographic indexing.

Why hex over rect: Cleaner dispersal kernels (no √2 axial-vs-diagonal asymmetry), 6-connectivity matches biological diffusion better, and H3’s hierarchical nesting allows running coarse-then-refined experiments without changing data formats.

Concrete tasks (after B is shipped):

| # | Task | Files | Days |
| --- | --- | --- | --- |
| C.1 | Add h3 dependency (Apache 2.0) | pyproject.toml | 0.25 |
| C.2 | HexGridTopology from a ocean-cell H3-id list | osmose/engine/hex_grid.py (new) | 3 |
| C.3 | Hex-aware random walk kernel | movement.py | 1 |
| C.4 | Hex-aware map-based movement: per-cell CSV format (cell_h3_id, prob) | movement.py + map readers | 2 |
| C.5 | Output writer: UGRID NetCDF for hex (or per-cell flat with H3 ids as a coord) | output.py | 2 |
| C.6 | UI: hex polygon layer (6-vertex polygons via h3-to-geo-boundary) | ui/pages/grid_helpers.py | 2 |
| C.7 | Forcing ingestion: regrid rectangular NetCDF → hex via area-weighted aggregation | osmose/engine/resources.py, background.py | 3 |
| C.8 | Movement-statistics parity: validate that walk-on-hex produces dispersion within ε of walk-on-rect for the same biological intent | tests/test_hex_movement_parity.py (new) | 4 |
| C.9 | Tooling: scripts/build_baltic_hex_grid.py — produce a hex equivalent of the Baltic mask | scripts/ | 2 |
| C.10 | Re-derive Baltic distribution maps on hex: 9 maps × ~0.5 day each | data/baltic/ | 5 |
| C.11 | End-to-end Baltic 50-y hex calibration parity check vs rectangular | tests/integration/ + run | 3 |
| C.12 | Documentation + tutorial | docs/ | 1 |

Effort: 28.25 person-days = ~6 weeks.

Pros: - Most ecologically-defensible non-rect option (uniform neighbor distance). - H3 dependency is industrial-strength. - Hierarchical resolutions enable scale studies “for free” once infrastructure exists.

Cons: - Distribution maps need rebuild from HELCOM/literature footprints (low-leverage but unavoidable). - Random walk semantics shift: walk_range=2 means different things on rect vs hex; per-species walk_range likely needs recalibration. - Forcing regridding (rect→hex) introduces small numerical noise vs the rectangular reference.

When to pick: if the modelling motivation is dispersal-kernel correctness or running scale studies (e.g., what does Baltic look like at H3 res 5 vs 6?). Less compelling if the motivation is coastal refinement (Option D handles that better) or external coupling (Option A is sufficient).

## 4 · Option D — Unstructured UGRID mesh (depends on B + C tooling)

What it ships: An UnstructuredGridTopology that reads a UGRID-CF NetCDF describing arbitrary polygon cells (triangles, quads, Voronoi cells). Mesh generation is out of scope — we consume meshes produced by gmsh, jigsaw, or OceanMesh2D.

Why FEM: regional refinement. Lagoons (Vistula, Curonian, Pärnu, Gulf of Riga) currently sit in 1–4 cells of the 0.4°×0.3° rectangular grid; with a refined mesh they can have 50+ cells while the open-Baltic basin keeps the same coarse cell count. This is the only path to multi-resolution within OSMOSE.

Concrete tasks (after B is shipped, ideally after C for tooling reuse):

| # | Task | Files | Days |
| --- | --- | --- | --- |
| D.1 | Add uxarray (LGPL-3.0) or hand-rolled UGRID reader | pyproject.toml, osmose/engine/ugrid_io.py (new) | 4 |
| D.2 | UnstructuredGridTopology with ragged neighbor table (CSR-style) | osmose/engine/unstructured_grid.py (new) | 5 |
| D.3 | Random walk: graph-step vs km-distance modes; precomputed neighbor distances | movement.py | 4 |
| D.4 | Map-based movement: per-cell-ID CSV; back-compat detection vs 2D rect | movement.py | 2 |
| D.5 | Output writer: full UGRID-CF emission with face_node_connectivity etc. | output.py | 4 |
| D.6 | UI: arbitrary-polygon layer; per-cell vertex count varies | ui/pages/grid_helpers.py | 3 |
| D.7 | Mesh-quality validation: closed mesh, no degenerate cells, ocean-extent matches | osmose/engine/ugrid_validation.py (new) | 2 |
| D.8 | Forcing regridder: rect/curvilinear NetCDF → unstructured (area-weighted) | resources.py, background.py | 5 |
| D.9 | Pipeline doc: how to generate a Baltic mesh (gmsh + bathymetry inputs) | docs/recipes/baltic-mesh.md (new) | 2 |
| D.10 | Distribution map regen pipeline: HELCOM polygon → unstructured per-cell prob | scripts/regen_maps_unstructured.py | 5 |
| D.11 | End-to-end refined Baltic mesh: e.g., 0.4° offshore, 0.05° in lagoons | data/baltic_unstructured/ | 8 |
| D.12 | Performance audit: 10k unstructured cells vs 2k rect cells (benchmarks + UI render) | tests/perf/ | 3 |
| D.13 | Documentation, tutorial, examples | docs/ | 3 |

Effort: 50 person-days = ~10 weeks = ~2.5 months, plus realistic-mesh build of ~2–4 weeks (collaboration with HELCOM bathymetry holders), so ~3–4 months calendar.

Pros: - Only path to coastal/lagoon refinement. - Aligns OSMOSE with modern coastal-ocean-model best practice. - UGRID is an open CF standard, so meshes are portable across tools.

Cons: - Largest engineering surface; mesh generation is upstream, mesh QA is on us. - All distribution maps require rebuild on the new mesh — that’s where most calendar time goes. - Performance: 10× more cells in lagoons may dominate runtime even though they hold 5% of biomass. - All Java parity gone; this is a research fork.

When to pick: only if Baltic-OSMOSE (or another regional config) needs lagoon/estuary resolution that rectangular grids cannot provide. Don’t pick this for “nice to have” — the calendar cost is real.

## 5 · Option E — Pre-processor only (no engine change)

What it ships: A standalone pipeline osmose/preprocess/mesh_to_rect.py that ingests a high-resolution mesh dataset (HELCOM bathymetry, ERA5 forcing, biological survey points, etc.) and aggregates it onto OSMOSE’s existing rectangular grid via area-weighted or point-in-polygon mapping. The engine is untouched.

Concrete tasks:

| # | Task | Files | Days |
| --- | --- | --- | --- |
| E.1 | Mesh reader (UGRID, gmsh .msh, ESRI shapefiles) | osmose/preprocess/mesh_io.py (new) | 2 |
| E.2 | Area-weighted aggregator: mesh field → rect cell | osmose/preprocess/aggregate.py (new) | 2 |
| E.3 | Point-cloud aggregator (e.g., HELCOM survey points → cell density) | osmose/preprocess/aggregate.py | 1 |
| E.4 | CLI wrapper: python -m osmose.preprocess.mesh_to_rect input.nc output.csv | scripts/mesh_to_rect.py | 1 |
| E.5 | Tests on Baltic ICES BITS hauls + HELCOM bathymetry | tests/preprocess/ | 2 |
| E.6 | Documentation cookbook: “use HELCOM data with OSMOSE” | docs/recipes/helcom-to-osmose.md | 1 |

Effort: 9 person-days = ~2 weeks.

Pros: - Zero engine risk. No regressions possible. - Java-parity preserved. - Solves the most common practical motivation (using HELCOM/ICES high-resolution data without forking the engine). - Complementary to all other options — the same pre-processor works on rect, hex, or unstructured engines.

Cons: - Doesn’t address dispersal-kernel correctness or coastal refinement in the engine. - Aggregation loses information; unwary users may misinterpret the results.

When to pick: unconditionally as a “Tier 0” deliverable. It costs ~2 weeks, has no risk, and immediately makes external data sources usable. Shipping E does not preclude any other option.

## 6 · Option F — Nested-rectangular subgrids (AMR-lite)

What it ships: Within an OSMOSE rectangular grid, designate one or more rectangular zones to be sub-divided at higher resolution. The engine internally treats the world as a union of rectangular sub-grids glued together at boundaries. Cells in the lagoon zone are 5× smaller; cells in the open Baltic stay coarse. No new topology library; arithmetic stays integer.

Why this might be attractive: delivers a key ecological motivation (coastal refinement) without leaving the rectangular world. Avoids hex/UGRID dependency entirely. Sits between B and D in cost.

Concrete tasks (after B):

| # | Task | Files | Days |
| --- | --- | --- | --- |
| F.1 | NestedRectGridTopology — a coarse base + N refinement zones | osmose/engine/nested_grid.py (new) | 3 |
| F.2 | Cell-ID scheme: contiguous flat IDs, with boundary-face mappings between levels | nested_grid.py | 3 |
| F.3 | Refinement-zone schema: grid.refine.zone.N.bbox, grid.refine.zone.N.factor | osmose/schema/grid.py | 1 |
| F.4 | Movement: cross-level cell transitions handled by neighbor table | movement.py | 3 |
| F.5 | Map-based movement: refine zones get inflated CSV submatrices; engine stitches | movement.py | 3 |
| F.6 | Forcing regrid: parent-cell value broadcast to children unless per-child file present | resources.py, background.py | 3 |
| F.7 | Output writer: nested NetCDF (group per refinement zone, or flat with cell_id coord) | output.py | 3 |
| F.8 | UI: render parent + child polygons with overlay; deck.gl handles the levels | ui/pages/grid_helpers.py | 2 |
| F.9 | Test fixture: 1 refinement zone in Baltic Vistula Lagoon | tests/test_nested_grid.py (new) | 3 |
| F.10 | Documentation + worked example | docs/recipes/nested-grids.md (new) | 1 |

Effort: 25 person-days = ~5 weeks.

Pros: - Solves coastal-refinement motivation without UGRID complexity. - Intermediate cost between B and D. - All math stays integer-arithmetic — fast and easy to optimize with Numba. - Distribution maps for refined zones can be regenerated only for those zones.

Cons: - Cell-boundary mass conservation is fiddly (movement crossing levels needs careful accounting). - Less standard than UGRID — not a recognized format, hard to share meshes with collaborators. - May not generalize: if you later need non-rectangular refinement (curved coastline), F doesn’t help and you’re back to D.

When to pick: the Baltic case really wants Vistula / Curonian / Gulf of Riga lagoon resolution but a) the team can’t take 3–4 months for D, and b) the refinement zones are clean rectangles or we’re willing to over-cover them.

## 7 · Cross-option engineering concerns

### 7.1 Distribution maps need regeneration on any non-rect topology

The 2026-04-21 work to differentiate Baltic distribution maps (sp4, sp5, herring spring/autumn, smelt spawning, life-stage containment) was done on rectangular cells. On hex/unstructured/nested grids each map needs rebuild from the source HELCOM polygons + literature. The pipeline is the same (point-in-polygon against a cell-center list) — only the cell-center list changes. Estimated ~5 person-days per topology if the pipeline is preserved.

### 7.2 Random walk semantics need a per-topology decision

walk_range=2 means a 5×5 box on rect, an H3 2-ring (~19 cells) on hex, and “graph distance ≤ 2” on unstructured. Biological intent (typical home-range size in km) doesn’t translate automatically. Recommendation: introduce a walk_range_km config key alongside the existing index-space walk_range, and let each topology convert. This is a one-time cost amortized across C, D, F.

### 7.3 Java parity is broken by A, C, D, F (preserved by B + E)

The Java OSMOSE engine is rectangular-only. Any engine-side topology beyond rectangular forks Python from Java numerically. This is strategic, not technical: are we still a parity port, or are we a divergent evolution? A clean answer here makes the option-selection matrix obvious. We have no current pressure to maintain parity (no recent reports of Python/Java divergence shipping production results), but historically parity has been valuable for cross-validation.

### 7.4 Multi-topology coexistence

Should the engine support both rectangular and hex configs in one binary, or is each topology a build-time choice? Recommendation: runtime dispatch via GridTopology protocol (Option B’s natural shape). The protocol cost is paid once; users pick at config-load time which topology to load.

### 7.5 Forcing & calibration

All currently-calibrated parameters (mortality, fishing, ingestion, fecundity) are per-species scalars and do not depend on grid topology. Switching topology does not invalidate the 2026-04-22 phase 1 / 2026-04-24 phase 2 / 2026-04-27 phase 12 calibration as a starting point. What needs regeneration: distribution maps, walk_range (if moving from index-space to km-space), and possibly LTL accessibility coefficients (since the spatial averaging implicit in rectangular grids breaks).

### 7.6 Performance

A 2,016-cell rectangular Baltic grid currently takes ~6 minutes for a 50-y sim under predator-active calibration contention. Estimated post-refactor / per-topology slowdowns:

- B alone: 0% (refactor only; numba-compiled hot paths unchanged).

- C (H3, ~5,000 cells at res 5): +20–30% (more cells, but flatter neighbor lookup).

- D (unstructured, ~10,000 cells with 5× refined lagoons): +100–150%, dominated by lagoon cells holding most schools post-spawning.

- F (nested rect, 1 zone at 5× refinement): +30–50%.

- E: zero engine impact (pre-processor).

These are guesses; performance spikes are needed before committing to D.

## 8 · Recommended sequencing

If we’re going to do this at all, the low-regret sequence is:

┌─ A (curvilinear)        ←  if NEMO/ROMS coupling motivated
   ┌─ E (pre-processor)  │
   │                     │
   │                     ├─ C (hex H3)             ←  if dispersal-kernel motivated
B ─┤                     │
   │                     ├─ D (unstructured)       ←  if coastal-refinement motivated
   │                     │
   └─ (status quo)       └─ F (nested rect)        ←  if coastal-refinement & rect-only world preferred

Concretely:

- Now (week 1–2): Ship E. ~2 weeks; immediate value; no engine risk; complementary to everything else.

- Now (week 1–4): Ship B. ~3 weeks; the prerequisite refactor; pays itself back in code clarity.

- Decision point (after B + E land): pick one of A, C, D, F based on the dominant motivation:

  - External-data coupling → A (1.5 wk).

  - Dispersal correctness / scale studies → C (6 wk).

  - Lagoon refinement, willing to take the calendar hit → D (3–4 mo).

  - Lagoon refinement, want to stay in rect-world → F (5 wk).

- The chosen option ships in its quoted timeline.

- Re-evaluate: did the new topology produce ecologically meaningfully different results, and are users actually picking it? Greenlight or shelve.

## 9 · Decision criteria (to fill in before committing)

Answer these before picking an option:

| Question | A | B | C | D | E | F |
| --- | --- | --- | --- | --- | --- | --- |
| Do we accept Java-parity divergence? | required | NO | required | required | NO | required |
| Is there a concrete external dataset we want to consume? | strong-yes | irrelevant | helpful | helpful | strong-yes | helpful |
| Is dispersal-kernel correctness the motivation? | no | no | yes | yes | no | no |
| Is coastal-lagoon resolution the motivation? | no | no | partial | yes | no | yes |
| Calendar budget available | 2 wk | 3 wk | 2 mo | 4 mo | 2 wk | 5 wk |
| Distribution-map regen acceptable | no | no | yes (5 days) | yes (5 days+) | no | yes (1 zone) |

## 10 · Risks & open questions

- Strategic risk (high impact): Java parity. A unilateral fork without an explicit agreement could surprise users. Resolve before any engine-side option (A, C, D, F).

- Schedule risk (medium impact): D’s 3–4 month estimate is optimistic; mesh QA + distribution-map regen frequently slip. Budget +50% on D.

- Performance risk (medium impact): D unstructured-mesh perf has not been benchmarked. Spike a 50-y Baltic-on-mesh run in week 2 of D before committing the rest of the engineering.

- Calibration risk (medium impact): Walk-range semantics shift. Plan a per-species walk_range recalibration as part of any topology switch (1 week of compute, embedded inside C/D/F’s calendar).

- Open question: Is the Baltic team’s actual unmet need coastal refinement (favors D/F) or external-data coupling (favors A/E)? This drives the option choice and should be answered in conversation, not in a planning doc.

- Open question: Does HELCOM publish UGRID-format Baltic bathymetry meshes? If yes, D becomes much cheaper. If no, mesh-generation upstream cost is real.

## 11 · What this plan does NOT decide

- Whether to do any of this. The status quo (rectangular only, parity-port to Java) is a coherent option.

- The exact H3 resolution (Option C). Suggest spike at res 5, 6, 7 and pick based on cell count + UI render time.

- Mesh-generation tooling for Option D — gmsh vs OceanMesh2D is itself a multi-day evaluation.

- Whether to expose topology selection in the Shiny UI (probably yes, but UI work is bundled into each option’s tasks).

## 12 · References

- 2026-04-24 feasibility study: docs/superpowers/specs/2026-04-24-non-rectangular-grids-exploration.md — survey of grid assumptions in the codebase + cost-per-subsystem table.

- UGRID CF convention: https://ugrid-conventions.github.io/ugrid-conventions/

- H3 geospatial indexing: https://h3geo.org/

- uxarray library: https://uxarray.readthedocs.io/

- gmsh mesh generator: https://gmsh.info/

- OceanMesh2D (MATLAB / Python mesh generator for coastal models): https://github.com/CHLNDDEV/OceanMesh2D

- Existing OSMOSE-Python grid code: osmose/engine/grid.py, osmose/engine/processes/movement.py, ui/pages/grid_helpers.py, osmose/schema/grid.py.

Author note: this document is a planning artifact, not a design spec. The expected next step is a 30-minute conversation to answer the §9 decision-criteria table, after which 1 or 2 options become obviously correct.